## Project Schedule
UltiMeeT Backend Functionality Development Schedule
SL. NO | Feature/Component | Phase | Planned Start Date | Planned End Date | Status | Comments
1 | FR1: Voice Biometric-Based Speaker Identification - The system should have the ability to identify speakers during both online and physical meetings using voice biometrics. This identification should be accurate and be able to distinguish between different individuals present in the meeting, thereby enabling precise attribution of statements or comments during the meeting. | Phase1 |  | 2023-06-19 | In Progress | RnD
2 | FR2: Automatic Meeting Recording and Transcription - The system should automatically record all meetings and transcribe them into text format. The transcription should be accurate and should include timestamps to identify when specific statements were made during the meeting. The system should also provide an option for playback of the recorded meeting. | Phase1 |  | 2023-06-19 | In Progress | Transcript Ready But Speaker Identification not done
3 | FR3: Integration with Email and Meeting Tools - The system should integrate seamlessly with popular email and meeting tools such as Microsoft Outlook, Google Workspace, Zoom, Microsoft Teams, etc. This integration should facilitate easy scheduling and management of meetings from within these popular platforms. | Phase1 | 2023-06-20 | 2023-06-23 |  | Email integration
4 | FR4: Customizable Meeting Templates - The system should offer customizable meeting agenda and minutes templates. Users should be able to modify these templates to suit their specific meeting requirements, and these templates should be storable for future use. | Phase1 | 2023-07-15 | 2023-07-18 |  | 5 templates
5 | FR5: Approval of Meeting Minutes - The system should provide a feature to easily approve meeting minutes by different stakeholders. This feature should include options for approval, modifications, or rejection of the minutes and action items on the individual. Notifications should be sent to relevant stakeholders when the minutes are ready for approval. | Phase1 | 2023-07-12 | 2023-07-15
6 | FR6: Task Management - The system should include features for tracking action items and managing tasks that arise from meetings. This feature should include tracking the status of tasks, assigning tasks to individuals, setting deadlines, and sending notifications for pending tasks. | Phase1 |  | 2023-07-15
7 | FR7: Meeting Summarization - The system should be able to provide a summarized version of the meeting for proxy attendees or for those who want to quickly understand the key points discussed in the meeting. The summarization should accurately represent the important discussions and decisions made during the meeting. | Phase1 | 2023-06-28 | 2023-06-30
8 | FR8: Audio and Text Search - The system should provide a feature to search the full audio and text transcriptions of the meetings. This feature should enable users to easily find specific statements or discussions made during any past meetings. | Phase1 | 2023-07-03 | 2023-07-05
9 | FR9: Automatic Sending of Meeting Minutes (MOM) - The system should automatically send the minutes of the meeting (MOM) to all stakeholders once the minutes are approved. This feature should include the ability to send MOMs via email or other communication platforms like Slack, Microsoft Teams, etc. | Phase2
10 | FR10: Customizable Access Control - The system should allow the meeting host or admins to customize access control for both internal and external stakeholders. This feature should allow control over who can view, edit or download the meeting recordings and minutes. | Phase1 | 2023-07-16 | 2023-07-20
11 | FR11: Meeting Matrices, Analytics and Insights -
| The system should be capable of providing analytics for individual and series of meetings. This includes data such as meeting duration, participation levels, action items completed and more. Insights gleaned from these data should be presented in an easy-to-understand format to aid in improving meeting efficiency. | Phase1 | 2023-07-11 | 2023-07-15
12 | FR12: Automatic Follow-Up Meeting Scheduling -
| The software should facilitate automatic scheduling of follow-up meetings based on the discussions and decisions made in prior meetings. This should include proposed times, draft agenda items and attendees. | Phase1 |  | 2023-07-15
13 | FR13: Alerts, Notifications, and Follow-Ups -
| The system should enable automatic alerts, notifications and follow-ups for action item owners. This could involve reminders of upcoming deadlines, updates on action item progress and notifications of new action items assigned. | Phase1 | 2023-06-25 | 2023-06-28
14 | FR14: Automatic Generation of PowerPoint Presentations -
| The software should be able to automatically generate PowerPoint presentations from previous meeting discussions, thus making it easier for users to review or present meeting outcomes. The presentations should be editable and customizable. | Phase2
15 | FR15: Team Collaboration Features -
| The software should provide features that facilitate team collaboration. This could include shared workspaces, collaborative editing of documents or a chat feature for real-time communication during meetings. | Phase2
16 | FR16: Integration with a CEO Cockpit -
| The system should be capable of integrating with a CEO cockpit (a comprehensive dashboard for CEO to view status of all meetings), thereby providing high-level overview and decision-making tools for company executives. | Phase2
17 | FR17: Attachment and Linking Capabilities -
| The system should allow for attachments to be added to meetings, agendas and minutes. It should also enable links between different applications and tools, allowing for seamless navigation between them. | Phase1 | 2023-07-15 | 2023-07-17
18 | FR18: Daily CXO Meeting Summaries -
| The software should provide daily meeting summaries in audio/video format specifically designed for CXOs to review during their commutes (while driving to office or going back home). These summaries should be brief, informative, and highlight key points and action items from the meetings. | Phase1 | 2023-07-05 | 2023-07-07
19 | FR19: Intelligent Agenda Creation -
| The software should be capable of intelligent agenda creation for CXOs based on calendar and previous MOMs. This could include suggesting topics for discussion, identifying key decision points and highlighting important action items. | Phase1 | 2023-07-05 | 2023-07-07
20 | FR20: Automatic Phone Call Scheduling -
| The system should facilitate automatic phone call scheduling to stakeholders using gathered intelligence. This feature could be used to arrange follow-up discussions, provide updates, or clarify points from meetings. | Phase2
21 | FR21: Integration with Planned Vacations and Travel Plans -
| The system should have a smart assistance feature that integrates with users' vacation and travel plans, allowing it to automatically adjust meeting schedules and reminders based on these plans. | Phase2
22 | FR22: Pending Approval Reminders -
| The system should be capable of sending reminders for pending approvals to CXOs across various applications, ensuring no essential approvals are missed or delayed. | Phase2
23 | FR23: Meeting Preparation Points for CXOs -
| The software should provide a summarized agenda and key points for CXOs to help them prepare for meetings efficiently. These preparation points should be tailored based on the meeting type and the participants involved. | Phase1 | 2023-07-05 | 2023-07-07
24 | FR24: Compatibility with Various Meeting Types -
| The software should be compatible with various meeting types, including Agile Scrum, project management, customer reviews and board meetings. This includes support for the specific processes and documentation associated with each meeting type. | Phase1 |  |  |  | Point covered
25 | FR25: AI-Assisted Meeting Facilitation -
| The software should provide AI-assisted facilitation to keep discussions on track and focused during meetings. This could involve providing real-time meeting summaries, prompting discussion of specific agenda items or suggesting follow-up action items. | Phase2
26 | FR26: Sentiment Analysis -
| The software should provide sentiment analysis features to gauge team morale and engagement during meetings. This could be based on participants' speech and language during meetings, or their responses to in-meeting polls or surveys. | Phase1 | 2023-07-02 | 2023-07-04
27 | FR27: Time Tracking -
| The system should provide time tracking features to ensure efficient meeting durations and adherence to schedules. This could involve setting a timer for each agenda item or providing a total meeting duration counter. | Phase2
28 | FR28: Multi-Language Support -
| The software should provide support for multiple languages, enabling global team collaboration and accurate transcription of multilingual meetings. This should include both the user interface of the software and the AI transcription feature. | Phase1 |  |  |  | R&D (3rd Party API)
29 | FR29: Recap of Meetings | Phase1 |  | 2023-07-28